## Sheet1
Sprint 2 - Backlog (Team 4)
Sprint 2: Task Description | Duration (Hours) | Member(s) | Status | Mon | Tues | Wed | Thurs | Fri
1. Debug existing application
Correct numbers for accurate shares | 1 | Thomas, Victor |  | 1 | 0 | 0 | 0 | 0
Make text smaller to fit on screen | 1 | Mark, Hamish |  | 1 | 0 | 0 | 0 | 0
Test code on physical Android Device | 1 | All |  | 1 | 0 | 0 | 0 | 0
3. Updates Views
Research graph api's for java android | 2 | All | Completed | 0 | 0 | 0 | 0 | 0
Research how to collect historic data from yahoo api | 2 | Adam, Peter | Completed | 0 | 0 | 0 | 0 | 0
Learn how to use new library | 2 | All | In Progress | 2 | 0 | 0 | 0 | 0
Plan how to implement this feature | 1 | Mark, Hamish | To Do | 1 | 1 | 1 | 1 | 1
Code the feature | 4 | Thomas, Mark | To Do | 4 | 4 | 4 | 4 | 4
Test code with sets of data | 2 | All | To Do | 2 | 2 | 2 | 2 | 2
|  |  | Totals: | 12 | 7 | 7 | 7 | 7

## Sheet2
Members | Status
Tom | To Do
Mark | In Progress
Victor | Completed
Pete
Adam
Hamish