## Sheet1
Sprint 2 - Backlog (Team 4)
Sprint 2: Task Description | Duration (Hours) | Member(s) | Status | Mon | Tues | Wed | Thurs | Fri
1. Debug existing application
Become familiar with the code | 2 | All | Completed | 1 | 0 | 0 | 0 | 0
Get application running on physical Android Device/Emulator | 2 | All | Completed | 1 | 0 | 0 | 0 | 0
Connect to Yahoo! Finance API | 1 | Thomas | Completed | 1 | 0 | 0 | 0 | 0
Get all Share Names displaying properly | 1 | Thomas | Completed | 1 | 0 | 0 | 0 | 0
Test code on physical Android Device | 1 | Victor, Adam, Thomas | Completed | 1 | 0 | 0 | 0 | 0
2. Sorting Shares
Create Hashmap to store Share Names and Overall Value | 1 | Thomas, Mark | Completed | 1 | 0 | 0 | 0 | 0
Create TreeMap to sort shares by highest value | 1 | Thomas, Adam | Completed | 1 | 0 | 0 | 0 | 0
Create NavMap to sort values into descending order | 1 | Thomas | Completed | 1 | 0 | 0 | 0 | 0
Increase readability | 2 | Victor, Mark | Completed | 2 | 2 | 0 | 0 | 0
Develop test data | 1 | All | Completed | 1 | 1 | 1 | 0 | 0
Perform test from story card | 2 | Victor, Hamish | Completed | 2 | 2 | 1 | 0 | 0
3. Updates Views
Research graph api's for java android | 2 | Hamish, Adam | Completed | 0 | 0 | 2 | 0 | 0
Research how to collect historic data from yahoo api | 2 | Mark, Victor | Completed | 0 | 0 | 2 | 0 | 0
Plan how to implement this feature | 2 | Thomas, Peter | In Progress | 0 | 0 | 2 | 2 | 1
Code the feature | 4 | Thomas, Peter | To Do | 0 | 0 | 4 | 4 | 4
Test code with sets of data | 2 | Mark, Victor | To Do | 0 | 0 | 2 | 2 | 2
|  |  | Totals: | 15 | 5 | 14 | 8 | 7

## Sheet2
Members | Status
Tom | To Do
Mark | In Progress
Victor | Completed
Pete
Adam
Hamish