## Sheet1
Sprint 1 - Backlog (Team 4)
[9 empty] | Tom | Mark | Victor | Pete | Adam | Hamish
Sprint 1: Task Description | Duration (Hours) | Member | Status | Mon | Tues | Wed | Thurs | Fri | To Do | In Progress | Completed
1. Debug existing application
Become familiar with the code | 2 | All | Completed | 0 | 0 | 0 | 0 | 0
Get application running on physical Android Device/Emulator | 2 | All | Completed | 0 | 0 | 0 | 0 | 0
Connect to Yahoo! Finance API | 1 | Tom | Completed | 0 | 0 | 0 | 0 | 0
Get all Share Names displaying properly | 1 | Tom | Completed | 0 | 0 | 0 | 0 | 0
Test code on physical Android Device | 1 | All | Completed | 0 | 0 | 0 | 0 | 0
2. Sorting Shares
Create Hashmap to store Share Names and Overall Value | 1 | Tom | Completed | 1 | 0 | 0 | 0 | 0
Create TreeMap to sort shares by highest value | 1 | Tom | Completed | 1 | 0 | 0 | 0 | 0
Create NavMap to sort values into descending order | 1 |  |  | 1 | 0 | 0 | 0 | 0
Develop test data | 1 | All | Completed | 1 | 0 | 0 | 0 | 0
Perform test from story card | 1 |  | Completed | 1 | 0 | 0 | 0 | 0

## Sheet2
Members | Status
Tom | To Do
Mark | In Progress
Victor | Completed
Pete
Adam
Hamish