## Sheet1
Sprint 2 - Backlog (Team 4)
Sprint 2: Task Description | Duration (Hours) | Member(s) | Status | Mon | Tues | Wed | Thurs | Fri | Mon | Tues | Wed | Thurs | Fri
1. Debug existing application
Correct numbers for accurate shares | 1 | Thomas, Victor | Completed | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Make text smaller to fit on screen | 1 | Mark, Hamish | Completed | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Test code on physical Android Device | 1 | Thomas, Victor | Completed | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2. Updates Views
Research graph api's for java android | 2 | All | Completed | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Plan how to collect historic data from yahoo api | 2 | Adam, Peter | Completed | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Learn how to use new AndroidPlot library | 2 | All | Completed | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Get library set up and running | 1 | Mark, Thomas | Completed | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Create new tab for 'Graphs', and code to run the tab activity | 0.5 | Thomas | Completed | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Create Spinners and populate with appropriate text | 1 | Hamish, Adam | Completed | 2 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Create a graph widget and plot a simple graph | 1 | Victor, Mark | Completed | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0
Plot lines using the historic data | 1 | Victor, Mark | Completed | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0
Adjust the aethetics of the graph widget | 6 | Victor, Mark | In Progress | 3 | 3 | 3 | 0 | 3 | 3 | 0 | 0 | 0 | 0
Test the spinners are altering the correct time periods | 0.5 | Peter, Adam | To Do | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0 | 0 | 0
Test the spinners are altering the correct company shares | 0.5 | Peter, Adam | To Do | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0 | 0 | 0
Test the graph is plotting lines relative to the time period and shares correctly | 0.5 | Peter, Adam | To Do | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0 | 0 | 0
3. JUnit Testing + Refactoring
Identify code to be refactored | 2 | All | To Do | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Refactor Feed Parser file | 3 | Peter, Adam, Hamish | To Do | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
Refactor Graph Activity file | 3 | Victor, Mark | To Do | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
Refactor Rockets file | 1 | Thomas | To Do | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
Refactor Alerts file | 1 | Thomas | To Do | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
|  |  | Totals: | 25 | 22 | 17.5 | 13.5 | 14.5 | 14.5 | 10 | 10 | 10 | 10

## Sheet2
Members | Status
Tom | To Do
Mark | In Progress
Victor | Completed
Pete
Adam
Hamish